## Sheet1
Heading | Line item | Comments following visit on 29/10/2024
Investigation works | Form hole at ground floor to inspect the basement area | Already undertaken. Accepted. | Agreed £ 650.00 is slightly over and above responsible costs. £ 350.00 | 350
| Test suspected asbestos containing materials | Accepted. | Agreed cost accetpable | 150
Remedial works | Promote rapid drying by opening the windows, operating 4x industrial sized dehumidifers and fans to dry damp affected areas | No evidence to support drying programme proposed but some level of drying would be expected. | Drying Costs £ 1,800.00 | 1800
| Assess timbers to all damp affected areas for signs of wood rot. This will include creating access to the ground floor void to allow the floor joists to be assessed and repairing access hole once assessed | Not necessary. | Not required already inspected | 0
| In non-structural timbers, allow to cut out and splice repair 10 No. 1 lin metres lengths of timber repairs to 300mm beyond the last sig of wet rot and splice in sections of unaffected, pre-treated timber | Not necessary. | Not required. | 0
Stip out | Carefully remove all damp affected floor coverings, insulation, ceilings, all fixtures and fittings generally to areas affected by reason of the works and remove from site | What areas are proposed here. The sum would suggest excessive action so not agreed. | Ceilings in bathroom, bedroom and landing to be removed only and re-plasterboarded aprrox 50 sq meters | 1500
Strip out ground floor | Strip out existing parquet flooring | Accepted to hallway only | Agreed 15 sq meters | 1000 | 31900 | 23900
| Strip out existing hardboard | The m2 proposed is excessive and unsupported | Hallway onty | 100
| Strip out existing floor tiles | Accepted | Kitchen | 650
| Strip out underfloor heating | Needs inspection and testing | Kitchen | 650
| Strip out hardboard | Accepted |  | 1400
| Remove existing carpet to staircase | Accepted |  | 750
| Remove damaged softwood flooring and fix new plain edge softwood flooring | kitchen only |  | 2300
| Hack of wall finishes with chipping hammer to plaster walls | Not Required |  | 0
| Strip of wallpaper use steam paper stripper - 3 layers | Not required |  | 0
| Remove lathe and plaster ceilings | Not Required |  | 0
| Remove skirtings | Bedroom /bathroom |  | 200
| Remove existing single doors | Not Required |  | 0
| Remove existing double doors | Not required |  | 0
| Remove defect kitchen worktops, cupboards and equipment | Not required |  | 2200
| Remove cloakroom bathroom | Not required |  | 0
| Remove large bathroom | First Floor bathroom |  | 2000
Strip out first floor | Remove damaged softwood flooring and fix new plain edge softwood flooring | Agreed |  | 2500
| 12 | Bathroom and bedroom only |  | 1200
| Strip of wallpaper use steam paper stripper - 3 layers | Bathroom bedroom only |  | 500
| Remove lathe and plaster ceilings | Bathroom bedroom hallway |  | 2750
| Remove skirtings | Accepted |  | 350
| Remove existing single doors | only 3 |  | 250
| Strip out existing family bathroom | Strip out and allow for new bathroom first floor |  | 10000
Strip out roof | Remove roof insulation | Accepted |  | 200
| Remove hardwood boarding | Accepted |  | 200
| Allow to strip back roof coverings and create access point to remove 3 No roof trusses (including for all temporary propping) and replace with matching roof trusses. Allow for replacing 40% of roof coverings with new due to impacted by reason of the works. | Not Required | 0 | 0
| Allowance for tin hat | Not Required | 0 | 0
Strip out mechanical and electrical installation | Allowance for removing the existing M&E installation | Not required - Report needed for the electrical system to confrim what works will be required | 1200 | 1200
Refurbishment ground floor | Supply and install new hardboard | Hallway only |  | 550
| Supply and install underfloor heating | The underfloor heating needs testing |  | 500
| Supply and install new parquet flooring | Accepted |  | 8000
| Supply and install new tiled flooring | Accepted |  | 750
| Supply and install new carpet to staircase | Accepted |  | 3500
| Supply and install new ceilings | Not required |  | 0
| Supply and install single new doors | not required |  | 0
| Supply and install double new door | not required |  | 0
| Allowance for works to kitchen | Kitchen worse case replace |  | 15000
| Allowance for new small bathroom | Not required |  | 0
| Allowance for larger bathroom | Not required |  | 0
| Allowance for remedial works under the staircase | Not required |  | 0
Refurbishment first floor | Sand and seal existing flooring | Agreed |  | 5850
| Supply and install new ceilings | Not Required |  | 0
| Supply and install single new doors | Not required |  | 0
| Allowance for new family bathroom | Accepted |  | alreadinclused above
Refurbishment roof | Provide and install mineral wool roll insulation to all areas of the loft to a depth of 270mm. Contractor should allow for laying one roll between the joists and rolls required to meet the required depth laid across the ceiling joists. Ensure that adequate ventilation at soffits is provided. We have allowed for a joiner to install loft legs as required to raise the height of the loft floor to prevent the new insulation from being crushed and for alterations to ceiling hatch as required | Accepted | 1500 | 1500
| Provide and install 18mm tongue and groove chipboard loft flooring above newly insulated loft floor |  | 1500 | 1500
| Provide roof ladder | Not required not broken | 0 | 0
Refurbishment generally | Where plaster has been removed to allow for the installation of new electrical cables, allow for filling in chases with British Gypsum Thistle Hardwall Plaster in strict accordance with the manufacturer’s instructions. Finishing plaster to be finished neatly and flush with surrounding plaster | bedroom only hall bathroom only |  | 3000
| Where ornate coving between the ceiling and wall abutment has been affected by damp or reason of the works is to be removed and replaced like for like | bedroom only |  | 1500
| Contractor is to prime newly plastered surfaces with 1 mist coat of Armstead Trade Diamond Eggshell of appropriate shade thinned up to 1-part clean water to 10 parts of product as appropriate | Bathroom bedroom hallway kitchen |  | 500
| Contractor is to allow for redecorating all areas affected by reason of the works to the next natural break/sight line. This is to include the entire wall if there is no convenient break line | Bathroom bedroom hallway kitchen |  | 2000
| Install skirting boards to all areas that have received new floor coverings | Approximately hallway and kitchen |  | 500
Mechanical and electrical works | Allow to fully re-wire property and replace all damaged light fittings. | Damaged light fittings only in the bedroom and bathroom |  | 2500
| Allow to commission boiler by gas safe registered engineer | Agreed |  | 750
| Allow for replacement boiler if damaged by water ingress | Agreed depending on results of gas engineer report |  | 4500
| Allow to replace and repair existing hot/cold water system where damaged that caused original leak | Inspection required |  | 5000
91600